NORTHSTAR AI

Beacon Launch Plan

| Department | Marketing | Owner | Priya Shah, VP Marketing |
| --- | --- | --- | --- |
| Date | March 3, 2026 | Status | Approved |
| Related Product | Beacon | Classification | Internal - fictional demo |

# Launch goal

Launch Beacon to mid-market knowledge-management buyers on June 16, 2026. The campaign will show how employees can find policy, product, and operational information without knowing exact filenames.

# Launch phases

| Phase | Timing | Key work | Owner |
| --- | --- | --- | --- |
| Prepare | March-April | Finalize messaging, demo library, and sales training. | Priya Shah |
| Pilot proof | April-May | Collect feedback from three fictional design partners. | Elena Rossi |
| Launch | June | Webinar, website release, analyst briefings, and customer email. | Priya Shah |
| Expand | July-September | Publish search use cases and partner enablement. | Priya Shah |

# Key messages

Find the right document even when you remember only the topic.

Get a concise answer with links to the underlying company sources.

Respect existing SharePoint permissions and content ownership.

# Launch budget

Beacon launch activities carry a planned 2026 marketing spend of $171,000 across webinar production, launch content, partner enablement, and digital demand generation. Detailed budget and actual spending are recorded in FY2026 Marketing Budget.xlsx.

# Readiness approvals

Elena Rossi approves product claims and demonstration behavior.

Priya Shah approves campaign assets and launch sequencing.

Rachel Stein approves total launch spending and changes above $15,000.

Sarah Kim reviews internal policy examples for accuracy.